## Sheet1
Weekly Production Plan
Planned Quantity |  | 1528 |  | Produced Quantity |  |  | 490 |  | 32.07%
100%
No. | Category | Customer Name | Product Name | Planned Quantity | Process | Number of People | Start Date | End Date | Work Hours (Days) | Mon 6/30 |  | Tue 7/1 |  | Wed 7/2 |  | Thu 7/3 |  | Fri 7/4 |  | Sat 7/5 |  | Sun 7/6 |  | Actual Production Quantity | Status | Remarks
[10 empty] | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual
1 | Outsourced | Customer 1 | Item 1 | 100 |  | 2 | 2021-06-30 | 2021-07-02 | 3 | 35 | 35 | 35 | 35 | 30 | 30 | [8 empty] | 100 | Completed
2 | Outsourced | Customer 2 | Item 2 | 100 |  | 2 | 2021-06-30 | 2021-07-03 | 4 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | [6 empty] | 100 | Completed
3 | Plug-in | Customer 3 | Item 3 | 100 |  | 2 | 2021-06-30 | 2021-07-04 | 5 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 |  |  |  |  | 100 | Completed
4 | Plug-in | Customer 4 | Item 4 | 100 |  | 1 | 2021-07-01 | 2021-07-05 | 5 |  |  | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 |  |  |  | 80 | Not Completed
5 | Plug-in | Customer 5 | Item 5 | 100 |  | 2 | 2021-07-02 | 2021-07-06 | 5 |  |  |  |  | 20 | 20 | 20 | 20 | 20 | 20 | 20 |  |  |  | 60 | Not Completed
6 | Plug-in | Customer 6 | Item 6 | 100 |  | 2 | 2021-07-03 | 2021-07-06 | 4 | [6 empty] | 25 | 25 | 25 | 25 | 25 |  |  |  | 50 | Not Completed
7 | Plug-in | Customer 7 | Item 7 | 100 |  | 3 |  |  | 1 | [14 empty] | 0 | Not Completed
8 | Plug-in | Customer 8 | Item 8 | 100 |  | 2 |  |  | 1 | [14 empty] | 0 | Not Completed
9 | Plug-in | Customer 9 | Item 9 | 101 |  | 3 |  |  | 1 | [14 empty] | 0 | Not Completed
10 | Plug-in | Customer 10 | Item 10 | 102 |  | 4 |  |  | 1 | [14 empty] | 0 | Not Completed
11 | Plug-in | Customer 11 | Item 11 | 103 |  | 5 |  |  | 1 | [14 empty] | 0 | Not Completed
12 | Plug-in | Customer 12 | Item 12 | 104 |  | 6 |  |  | 1 | [14 empty] | 0 | Not Completed
13 | Plug-in | Customer 13 | Item 13 | 105 |  | 7 |  |  | 1 | [14 empty] | 0 | Not Completed
14 | Plug-in | Customer 14 | Item 14 | 106 |  | 8 |  |  | 1 | [14 empty] | 0 | Not Completed
15 | Plug-in | Customer 15 | Item 15 | 107 |  | 9 |  |  | 1 | [14 empty] | 0 | Not Completed
[9 empty] | 1 | [14 empty] | 0 | Completed
[9 empty] | 1 | [14 empty] | 0 | Completed
[9 empty] | 1 | [14 empty] | 0 | Completed
[9 empty] | 1 | [14 empty] | 0 | Completed
[9 empty] | 1 | [14 empty] | 0 | Completed